| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Best Practices for the Prevention of Corrosion of Department of Transportation Equipment: A User’s Manual OBJECTIVES: This project will develop best practice guidelines using the information provided in the Phase I report and other relevant sources. The end result would be an easy-to-use guide that summarizes in layman’s terms the best practices to prevent corrosion to maintenance equipment. |  |  |
| PERIOD COVERED: Apr. 1, 2014 – June 30, 2014 |  |  |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime Monte Vista Associates LLC, Arizona - Subcontractor |  |  |
| PROJECT MANAGER: Tom Peters LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Xianming Shi, Ph.D., P.E. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $49,950 | PROJECT EXPENDITURES TO DATE: $40,596 |  |
| WORK COMPLETED: Task 0. Project Management (90% Completed) A kick-off meeting was held with the project panel via teleconference on June 26, 2014 to discuss the project progress and next steps. Task 1: Review and Analyze Research (100% completed) The researchers have compiled, reviewed, and analyzed the results of the Phase I final report (Best Practices and Guidelines for Protecting DOT Equipment from the Corrosive Effect of Chemical Deicers) and other relevant research that focuses on chloride corrosion. (Inhibitor blends are not a focus in this study). Recent research conducted by international sources were reviewed wherever available, along with the ongoing research and existing documents published by the Department of Defense (DoD), National Association of Corrosion Engineers (NACE), automotive/trucking industry, Departments of Transportation (DOTs), etc. The review has supplemented the one conducted in Phase I and focused on recent literature and literature useful for developing the user’s guide or manual. Task 2: Develop a Manual (80% completed) Utilizing information from Task 1, the team has developed a user-friendly manual that documents best practices of managing the risk of equipment corrosion, especially in the presence of chemical deicers. This manual will serve as a “living document” that can be readily implemented and updated after the completion of this project. The audience for this manual will be operators, mechanics and garage-level supervisors. Readers will not have higher than a high school diploma and the manual will be written to avoid chemical jargon. The manual will focus more on instruction and less on the science behind corrosion. Task 3. Final Report and Presentation (70% completed) |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will mainly consist of Task 2 (Develop a Manual), including the outreach to practitioners/agencies for suitable photos to be included in the manual. A request for photos etc. has been distributed thru Clear Roads to the identified State DOTs. The work this quarter will focus on incorporating the DOT photos and making the draft manual more reader-friendly. |  |  |
| STATUS AND COMPLETION DATE: The project is on schedule but there is a significant risk of budget overrun as the manual development has taken more time than originally anticipated and also there is the upcoming transition of the PI from WTI to Washington State University. Completion date – Dec. 31, 2014 |  |  |