| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Cost-Benefit Analysis Toolkit – Phase II OBJECTIVES: To expand upon and improve the winter maintenance cost/benefit analysis toolkit Phase I. |  |  |
| PERIOD COVERED: April 1, 2012 – June 30, 2012 |  |  |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime Current Transportation Solutions Inc. - Consultants |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Xianming Shi, Ph.D., P.E. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $109,999 | PROJECT EXPENDITURES TO DATE: $22,740 |  |
| WORK COMPLETED: Project Management A project meeting (via teleconference) was held on June 26, 2012 to allow the PI to report the project progress to the project TAC and to discuss next steps. Task 1. Phase I Enhancements (95% completed) A contracted service agreement was executed for MSU to hire the Current Transportation Solutions Inc. (CTS) as consultants on this project. The CTS team has implemented all the Phase I enhancements outlined in the contract and the new toolkit link was distributed to the TAC for test drive. The enhancements mainly include: ensuring the tool runs on more versions of Internet browsers and generating reports in a format that can be more easily manipulated for presentation to managers. The enhanced toolkit also includes the capability of allowing a user to save multiple scenarios and revisit them. We also include some photos for items in this toolkit to enhance its usability. Task 2. Survey to Identify Another Ten Items (100% completed) The research team has prioritized the new top ten items for this toolkit via a survey of practitioners. This includes practices that are frequently used, along with newer and possibly less understood but promising practices. We designed and distributed a survey to gather information from the 25 Clear Roads member states and other winter maintenance professionals to determine the next ten most important materials, equipment or methods on which the TAC would like to be able to perform a cost-benefit analysis using the toolkit. The research team worked with the TAC to determine final list for Phase II development. Some items suggested for consideration in Phase II development by the TAC include: - Comparing flexible blades to traditional blades - Pre-wetting at the spreader - Slurries - Plow guards - Spreader calibration - Tow plows - Open vs. closed loop spreader controls - Laser guides - Abrasives (sand/aggregates in different types or weights/sizes) - Remote cameras for monitoring remote sites locations - Contracted truck (private or municipal) versus a state-owned truck - Tailgate vs. hopper spreaders Task 3. Data Elements for Cost-Benefit Analysis (20% completed) The research team has gathered some data for the new top ten items needed for cost-benefit analysis. We will continue to contact appropriate contacts identified in Task 2 to complete this task. Task 4. Methodologies and Assumptions for Cost-Benefit Analysis (0% completed) Task 5. Website Implementation and User’s Guide (0% completed) Task 6. Final Report/Presentation/Training Session (0% completed) |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will consist of three tracks. First, a concise memorandum of findings from Task 1 will be submitted. June 2012 Second, we will complete. Secondly, work will continue for Task 3. Data Elements for Cost-Benefit Analysis. Finally, work will start on Task 4. Methodologies and Assumptions for Cost-Benefit Analysis. |  |  |
| STATUS AND COMPLETION DATE: On time and on schedule. Start and completion dates of this project: Feb. 6, 2012 - Jan. 31, 2013. |  |  |