| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Understanding the True Cost of Snow and Ice Control OBJECTIVES: Create a tool to communicate the maintenance level of service that can be bought by different budget levels. Compare at a high level the true cost of winter maintenance experienced at an aggregate level by states. |  |  |
| PERIOD COVERED: January 1, 2012 to March 30, 2012 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Patrick Hughes, Parsons Brinckerhoff | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $192,720.23 | PROJECT EXPENDITURES TO DATE: $20,075.05 |  |
| WORK COMPLETED: - Identified cost categories for analysis - Assessed data availability through multi-state survey - Began collecting, analyzing and consolidating data - Began assessing ability of data to support objectives and achieve results |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - Complete data collection and assessment - Revisit objectives if necessary to meet data availability - Begin development of prototype tool to meet objectives |  |  |
| STATUS AND COMPLETION DATE: This research projects is well underway in the data collection and assessment phase. Completion is expected December 2012. |  |  |